## Synopsis
Sr. No. | Developer Name | Issue count
1 | Anil | 4
2 | Dipali | 18
3 | Prakash | 53
4 | Prathamesh | 17
5 | Priya P | 11
6 | Swetha | 13

## Prepr
Sr. No. | Cover | Observation | Priority | Raised on | Developer Name | Resolved Date | Environment | Testing remark
1 | Cyber | Showing incorrect TAT in unassigned queue CYB000007336 | Medium | 2021-05-06 | Dipali |  | Preprod
2 | Cyber | Customer name & age is coming blank | Medium | 2021-05-06 | Phoenix |  | Preprod
3 | Cyber | When clicking Last few claim intimated and coming back to page, CSM assessment and Intimation details sections getting vanished | High | 2021-05-06 | Prakash |  | Preprod
4 | Cyber | When clicking open document next tab button, showing xml page | High | 2021-05-06 | Swetha |  | Preprod
5 | Cyber | Policy holder name is blank on document | Medium | 2021-05-06 | Swetha |  | Preprod
6 | Cyber | Sent query details not populating | Showstopper | 2021-05-06 | Prathamesh |  | Preprod
7 | Cyber | When CSM concludes and approves claim, no change happening in status of claim | Showstopper | 2021-05-06 | Prathamesh, Prakash |  | Preprod
8 | Cyber | When CSM concludes and rejects claim, no change happening in status of claim | Showstopper | 2021-05-06 | Prathamesh, Prakash |  | Preprod
9 | Cyber | Policy holder name is blank in Payout details | Medium | 2021-05-06 | Prakash |  | Preprod
10 | Cyber | On clicking Audit trail, showing error page | High | 2021-05-06 | Prakash |  | Preprod
11 | All covers | Showing istheclaimwithdraw as true in getclaimstatus API response(claim is not withdrawn) | Medium | 2021-05-06 | Prakash |  | Preprod
12 | Login | On clicking enter key, should login to application | Low | 2021-05-06 | Prakash |  | Preprod
13 | Cyber | "Policy is cancelled" deviation not working-claim not getting added into not to be assigned queue CYB000007342 | High | 2021-05-06 | Prathamesh
14 | Login | Randomly page getting log out and showing error on page | High | 2021-05-07 | Anil
15 | Missed Flight | Showing incorrect TAT in unassigned queue CYB000007336 | Medium | 2021-05-07 | Dipali |  | Preprod
16 | Missed Flight | Customer name & age is coming blank | Medium | 2021-05-07 | Phoenix |  | Preprod
17 | Missed Flight | When clicking Last few claim intimated and coming back to page, CSM assessment and Intimation details sections getting vanished | High | 2021-05-07 | Prakash |  | Preprod
18 | Missed Flight | When clicking open document next tab button, showing xml page | High | 2021-05-07 | Swetha |  | Preprod
19 | Missed Flight | Policy holder name is blank on document | Medium | 2021-05-07 | Swetha |  | Preprod
20 | Missed Flight | Sent query details not populating | Showstopper | 2021-05-07 | Prathamesh |  | Preprod
21 | Missed Flight | When CSM concludes and approves claim, no change happening in status of claim | Showstopper | 2021-05-07 | Prakash |  | Preprod
22 | Missed Flight | When CSM concludes and rejects claim, no change happening in status of claim | Showstopper | 2021-05-07 | Prakash |  | Preprod
23 | Missed Flight | Policy holder name is blank in Payout details | Medium | 2021-05-07 | Prakash |  | Preprod
24 | Missed Flight | On clicking Audit trail, showing error page | High | 2021-05-07 | Prakash |  | Preprod
25 | Missed Flight | Showing istheclaimwithdraw as true in getclaimstatus API response(claim is not withdrawn) | Medium | 2021-05-07 | Prakash |  | Preprod
26 | Missed Flight | On clicking enter key, should login to application | Low | 2021-05-07 | Prakash |  | Preprod
27 | Missed Flight | On selecting from the list of airlines company showing error page | Medium | 2021-05-07 | Prakash |  | Preprod
28 | Hospicash | Showing wrong TAT in unassigned queue HC000007353 | Medium | 2021-05-10 | Dipali |  | Preprod
29 | Hospicash | Customer name & age is showing as blank HC000007353 | Medium | 2021-05-10 | Phoenix |  | Preprod
30 | Hospicash | When clicking on Last few claims intimated View link and coming back to main page, Intimation details and CSM assessment details sections getting vanished | High | 2021-05-10 | Prakash |  | Preprod
31 | Hospicash | Sent query details not populating on page | Showstopper | 2021-05-10 | Prathamesh |  | Preprod
32 | Hospicash | When selecting Does the insured have PED? As Yes and filled details, after reopening saved data the filled details for Does the insured have PED? getting vanished | Medium | 2021-05-10 | Prakash |  | Preprod
33 | Hospicash | When CSM concludes and approves claim, status of claim not getting changed | Showstopper | 2021-05-10 | Prakash |  | Preprod
34 | Hospicash | When CSM concludes and rejects claim, no action getting performaed on claim i.e. status not changing, rejected box not present | Showstopper | 2021-05-10 | Prakash |  | Preprod
35 | Hospicash | When clicking on Audit trail, showing below error page | High | 2021-05-10 | Prakash |  | Preprod
36 | Hospicash | Account holder name is blank in Payout calculation | Medium | 2021-05-10 | Prakash |  | Preprod
37 | Hospicash | Policy holder name is blank on Document | Medium | 2021-05-10 | Swetha |  | Preprod
38 | Hospicash | When clicking open proof in next tab button, shows below xml page | High | 2021-05-10 | Swetha |  | Preprod
39 | Wyn Accident | Showing wrong TAT in unassigned queue PA000007356 | Medium | 2021-05-11 | Dipali |  | Preprod
40 | Wyn Accident | Customer name & age is showing as blank PA000007356 | Medium | 2021-05-11 | Phoenix |  | Preprod
41 | Wyn Accident | When clicking on Last few claims intimated View link and coming back to main page, Intimation details and CSM assessment details sections getting vanished | High | 2021-05-11 | Prakash |  | Preprod
42 | Wyn Accident | Sent query details not populating on page | High | 2021-05-11 | Prathamesh |  | Preprod
43 | Wyn Accident | When selecting Does the insured have PED? As Yes and filled details, after reopening saved data the filled details for Does the insured have PED? getting vanished | Medium | 2021-05-11 | Prakash |  | Preprod
44 | Wyn Accident | When CSM concludes and approves claim, status of claim not getting changed | Showstopper | 2021-05-11 | Prakash |  | Preprod
45 | Wyn Accident | When CSM concludes and rejects claim, no action getting performed on claim i.e. status not changing, rejected box not present | Showstopper | 2021-05-11 | Prakash |  | Preprod
46 | Wyn Accident | When clicking on Audit trail, showing below error page | High | 2021-05-11 | Prakash |  | Preprod
47 | Wyn Accident | Account holder name is blank in Payout calculation | Medium | 2021-05-11 | Prakash |  | Preprod
48 | Wyn Accident | Policy holder name is blank on Document | Medium | 2021-05-11 | Swetha |  | Preprod
49 | Wyn Accident | When clicking open proof in next tab button, shows below xml page | High | 2021-05-11 | Swetha |  | Preprod
50 | Critical Illness | Showing wrong TAT in unassigned queue CI000007358 | Medium | 2021-05-12 | Dipali |  | Preprod
51 | Critical Illness | Customer name & age is showing as blank CI000007358 | Medium | 2021-05-12 | Phoenix |  | Preprod
52 | Critical Illness | When clicking on Last few claims intimated View link and coming back to main page, Intimation details and CSM assessment details sections getting vanished | High | 2021-05-12 | Prakash |  | Preprod
53 | Critical Illness | Sent query details not populating on page | High | 2021-05-12 | Prathamesh |  | Preprod
54 | Critical Illness | Document checklist not present | High | 2021-05-12 | Prathamesh/Swetha |  | Preprod
55 | Critical Illness | When CSM concludes and approves claim, status of claim not getting changed | Showstopper | 2021-05-12 | Prakash |  | Preprod
56 | Critical Illness | When CSM concludes and rejects claim, no action getting performed on claim i.e. status not changing, rejected box not present | Showstopper | 2021-05-12 | Prakash |  | Preprod
57 | Critical Illness | When clicking on Audit trail, showing below error page | High | 2021-05-12 | Prakash |  | Preprod
58 | Critical Illness | Account holder name is blank in Payout calculation | Medium | 2021-05-12 | Prakash |  | Preprod
59 | Critical Illness | Policy holder name is blank on Document | Medium | 2021-05-12 | Swetha |  | Preprod
60 | Critical Illness | When clicking open proof in next tab button, shows below xml page | High | 2021-05-12 | Swetha |  | Preprod
61 | Mobile lite | Internal status of claim is CSM assessment but claim is not present under unassigned queue SD000007359 | Showstopper | 2021-05-13 | Prathamesh |  | Preprod
62 | Mobile lite | Customer name & age is showing as blank SD000007359 | Medium | 2021-05-13 | Phoenix |  | Preprod
63 | Mobile lite | When clicking on Last few claims intimated View link and coming back to main page, Intimation details and CSM assessment details sections getting vanished | High | 2021-05-13 | Prakash |  | Preprod
64 | Mobile lite | Blocked to test complete flow | Showstopper | 2021-05-13 | Dipali/Prathamesh |  | Preprod
65 | Mobile lite | Showing error downloading video file in Video processing of AI Assessment | High | 2021-05-13 | Swetha |  | Preprod
66 | Mobile lite | When clicking on Audit trail, showing below error page | High | 2021-05-13 | Prakash |  | Preprod
67 | Mobile lite | Not able to test Raise query functionality-due to claim assignment blocker | High | 2021-05-13 | Prathamesh |  | Preprod
68 | Mobile lite | Not able to test Claim conclusion functionality-due to claim assignment blocker | High | 2021-05-13 | Prakash |  | Preprod
69 | Mobile lite | Not able to test Proofs and Documents functionality-due to claim assignment blocker | High | 2021-05-13 | Swetha |  | Preprod
70 | Mobile lite | Not able to test AI Assessment functionality-due to claim assignment blocker | High | 2021-05-13 | Swetha |  | Preprod
71 | Mobile lite | Not able to test Payout calculation functionality-due to claim assignment blocker | High | 2021-05-13 | Prakash |  | Preprod
72 | Mobile lite | Not able to test Vendor assessment functionality-due to claim assignment blocker | High | 2021-05-13 | Dipali |  | Preprod
73 | OPD | After Saveprescription API hit, claim number not showing under unassigned queue of supervisor’s login- OPD000007360 | Showstopper | 2021-05-17 | Prakash |  | Preprod
74 | OPD | Customer name & age showing blank | Medium | 2021-05-17 | Phoenix |  | Preprod
75 | OPD | Edit details link of CSM assessment is clickable even after claim is searched from search claim menu | High | 2021-05-17 | Prakash |  | Preprod
76 | OPD | Unable to check View last claim history, due to claim assignment blocker | High | 2021-05-17 | Prakash/Dipali |  | Preprod
77 | OPD | Unable to test Proofs section due to claim assignment blocker | High | 2021-05-17 | Prakash/Dipali |  | Preprod
78 | OPD | On CSM assessment page, Date of consultation should be taken from Saveprescription API. Here it is showing current date | High | 2021-05-17 | Prakash/Dipali |  | Preprod
79 | OPD | When CSM assessment details data is filled and clicked on Save button, Balance sum insured in payout details is showing null | Medium | 2021-05-17 | Prakash/Dipali |  | Preprod
80 | OPD | Balance sum insured in Assessment history is showing 0-under Net payable table | Medium | 2021-05-17 | Prakash |  | Preprod
81 | OPD | Conclude button is not clickable, due to claim assignment blocker. Not able to proceed further to check Verification by Partner status | Showstopper | 2021-05-17 | Prakash |  | Preprod
82 | OPD | On clicking Audit trail, showing below error page | High | 2021-05-17 | Prakash |  | Preprod
83 | OPD | SKU id not reflecting on UI, instead sku id system showing SKU Name in SKU details of Assessment History | Medium | 2021-05-17 | Dipali |  | Preprod
84 | OPD | SKU id not present under Fetchcovered API response | Medium | 2021-05-17 | Dipali |  | Preprod
85 | OPD | Not covered details calculation showing 0 in Fetchcovered API response | Medium | 2021-05-17 | Dipali |  | Preprod
86 | OPD | Unable to test further flow from “Order confirmed” stage, due to claim assignment blocker CSM not able to conclude claim. Shows below error – | Showstopper | 2021-05-17 | Prakash/Dipali |  | Preprod
87 | OPD | Not able to check reserve functionality, due to claim assignment blocker | High | 2021-05-17 | Prakash/Dipali |  | Preprod
88 | OPD | Reporter details section not available under Claim intimation section | Medium | 2021-05-17 | Prakash/Dipali |  | Preprod
89 | OPD | Cancellation flows are not working-“ Customer not contactable”, “Customer initiated cancellation”, showing false API response OPD000007361 | High | 2021-05-17 | Prathamesh |  | Preprod
90 | Break | On clicking resume button of Break, showing Please enter correct password mesage on screen | High | 2021-05-17 | Dipali/Prakash |  | Preprod
91 | Break | When clicking on eye button to view entered password, label and entered password getting overlapped | High | 2021-05-17 | Dipali/Prakash |  | Preprod
92 | Break | When CSM is on break and while resume back getting error, but when he is clicking on close button on screen and checking back on main page then system shows CSM is online | High | 2021-05-17 | Dipali/Prakash |  | Preprod
93 | Break | Even when CSM clicked on Go on Break option but not selected any option and closed the popup, system shows CSM is on Break | High | 2021-05-17 | Dipali/Prakash |  | Preprod
94 | Dashboard | Date of intimation filter not working correctly, order is not ascending neither descending | Medium | 2021-05-17 | Prathamesh/Prakash |  | Preprod
95 | Dashboard | Claims to be assigned queue count for supervisor is incorrect i.e. in Menu it shows 97 where actual count is 84 | Low | 2021-05-17 | Anil/Prathamesh |  | Preprod
96 | Dashboard | Claims awaiting revert options don’t show count in menu | Low | 2021-05-17 | Anil/Prathamesh |  | Preprod
97 | Dashboard | System shows incorrect count for Teams claims i.e. actual count is 35 where in queue it shows 39 | Low | 2021-05-17 | Anil/Prathamesh |  | Preprod
98 | Dashboard | Shows error even when user is not working on that claim | High | 2021-05-17 | Dipali |  | Preprod
99 | Dashboard | Assign button and Calendar icon both got overlapped | Low | 2021-05-17 | ? |  | Preprod
100 | Dashboard | Calendar filter not working properly-All handled claims of CSM1. I selected date range from 1 March to 10 march but system shows Feb data as well | Medium | 2021-05-17 | Dipali |  | Preprod
101 | Dashboard | d alendar filter not working properly-All Approved claims of CSM1. I selected date range from 1 March to 10 march but system shows Feb data as well | Medium | 2021-05-17 | Dipali |  | Preprod
102 | Dashboard | When clicking calendar under performance history it shows disabled, on refresh page it get enabled | Medium | 2021-05-17 | Dipali |  | Preprod
103 | One View | First name, Last name, wyn policy No are blank for cust ID cust_Ih2Pnr3T1PpDAsb | Medium | 2021-05-17 | Priya P |  | Preprod
104 | One View | Personal details are blank in One View | High | 2021-05-17 | Priya P |  | Preprod
105 | One View | I have clicked on Payment menu, but page is stuck and not showing Payment page | High | 2021-05-17 | Priya P |  | Preprod
106 | One View | On clicking view inspection link from any of the inspection in list, shows blank page | High | 2021-05-17 | Priya P |  | Preprod
107 | One View | When clicking Policy menu, page stuck and Policy page doesn’t get open | High | 2021-05-17 | Priya P |  | Preprod
108 | One View | On clicking Claims option from menu, specified page not getting opened | High | 2021-05-17 | Priya P |  | Preprod
109 | One View | Cover information page showing blank data | High | 2021-05-17 | Priya P |  | Preprod
110 | One View | For claim status as CSM assessment showing amount in approved amount column which is incorrect | Medium | 2021-05-17 | Priya P |  | Preprod
111 | One View | Options from Menu gets vanished when user click on claim and come back on original page | Medium | 2021-05-17 | Priya P |  | Preprod
112 | One View | User name is blank, only showing options-Online, Go on Break, Sign out | High | 2021-05-17 | Priya P |  | Preprod
113 | One View | There is no field validation for IMEI num field on Inspection screen | Low | 2021-05-17 | Priya P |  | Preprod
Preprod