## task list
Month | WEEK | Project Name | CR / INTERACTION / TASK NAME | ASSIGNED TO | PRIORITY | Plan START Date (MM-DD-YY) | Plan END Date (MM-DD-YY) | Actual START Date (MM-DD-YY) | Actual END Date (MM-DD-YY) | No of Days Delayed | % COMPLETE | NOTES
DEC | 5 | ATLAS | Demo ENTRY | ABC | HIGH | 2021-12-01 | 2021-01-13 | 2020-12-18 | 2020-12-22 | -22 | 100% | ABC
| 5 | ATLAS | FT Integration | Vinod | HIGH | 2020-12-21 | 2021-01-15 | 2020-12-28 | 2021-01-19 | 2 | 80% | Pending with BatchStatus Error rectifiying Task to send error records in next batch