## Sheet1
S.no | Tasks | Status | % of completion |  | 2021-01-12 | Date
1 | SendAtlasdatatoFT API - atlas data to Ft via account details API | Completed | 100 | Priya P/Vinod | token involvement to Ft with authentication token | 12012021
2 | Payment ID creation for Batch Status Details API | Completed | 100 | Vinod | 2021-01-13
3 | Table creation to save response data from Accounting details API | Completed | 100 | Vinod | 2021-01-12
4 | Updating Atlas new fields in API (taking prathamesh's & Swetha help) | Completed | 100 | Priya P/Vinod | 12-01-2021 & 13-01-2021
5 | Updating SendAtlasdatatoFT API to send failure records to FT | Completed | 100 | Vinod | 2021-01-13
6 | Unit Testing | Completed | 100
7 | Table creation for Batch Status API details to store at Atlas | Completed | 100 | vinod | 2021-01-12
8 | Batch Status API creation | Completed | 100 | vinod | 2021-01-12
9 | Batch Status API response stroring | Completed | 100 | priya P / Vinod | 2021-01-12
10 | Unit Testing | Completed | 100
11 | SP Update required for second batch of records | Completed |  | vinod | 2021-01-13
12 | need to rectify the error from Batch status API response and add it to table | Not Started |  | vinod
13 | Database updates for new required SPs like get error records to insert into first API to send to FT | Completed |  | vinod
14 | Get the new fields data from Phoenix Team | Not Started
Pending Tasks at our end
1 | Error Handling for failure records to send in next batch | Not Started
2 | Set accurate for transactions in Atlas | Not Started

## Sheet3
should we send location for 31.?
Where do we get IL branch code for 31 postkey.?
Post

## Sheet2
One-View | Integration to call customers | Not Completed
One-View | Integration to fetch call recordings | Not Completed
One-View | Create API contracts to get customer and cover details | completed | Customer details aka Profile details
One-View | Payment and refunds | completed
One-View | Tickets | Not Completed
One-View | Documents | Not Completed
One-View | Integration of one-view in claim interface | NA | Claim History Completed
One-View | Cover information | completed